## Cronograma_AETHER_VITAE_es
Summary | Description | Assignee | Start date | Due date | Priority
Accreditation & Setup | Participant registration & laptop setup (Python, Git) | Todos | 2025-10-04 09:00 | 2025-10-04 09:30 | Media
Kickoff & Roles | Welcome session & roles division; initial Jira board setup for the hackathon | Víctor | 2025-10-04 09:30 | 2025-10-04 10:00 | Alta
Repository Creation | Create the repository on GitHub & configure the project in Jira | Oswaldo / Víctor | 2025-10-04 10:00 | 2025-10-04 11:00 | Alta
Data Loading & Cleaning | Load the dataset of 608 space biology articles & clean its fields | Miguel F | 2025-10-04 11:00 | 2025-10-04 12:30 | Alta
Tokenization & Categories | Tokenize texts & derive main categories from token frequency | Ángel | 2025-10-04 12:30 | 2025-10-04 13:30 | Media
Break & Mentoring | Lunch break & mentoring by event staff | Todos | 2025-10-04 13:30 | 2025-10-04 14:30 | Baja
Similarity Matrix | Generate the similarity matrix (−1, 0, 1) & compute cosine of term vectors | Óscar / Ángel | 2025-10-04 14:30 | 2025-10-04 16:30 | Alta
API Development | Develop the base API (FastAPI/Flask) for querying the articles | Óscar | 2025-10-04 16:30 | 2025-10-04 18:00 | Alta
Query Testing | Run test queries such as “DNA” & “plants” to validate the model | Oswaldo / Víctor | 2025-10-04 18:00 | 2025-10-04 19:00 | Media
Streamlit Interface | Implement the initial Streamlit interface for searching & displaying results | Oswaldo | 2025-10-04 19:00 | 2025-10-04 20:00 | Alta
Capsule Template | Create the NotebookLM template for informational capsules | Víctor / Isay | 2025-10-04 20:00 | 2025-10-04 21:00 | Media
Backup & Review | Back up the repository & review the first day’s progress | Todos | 2025-10-04 21:00 | 2025-10-04 22:00 | Baja
Synchronization & Issues | Synchronize the team & resolve pending issues before starting the second day | Todos | 2025-10-05 09:00 | 2025-10-05 09:30 | Media
Chatbot Integration | Integrate the chatbot with the Groq API (Llama3) for natural-language queries | Óscar / Ángel | 2025-10-05 09:30 | 2025-10-05 10:30 | Alta
Dashboard Development | Develop the dashboard with charts & filters to explore information | Oswaldo / Ángel | 2025-10-05 10:30 | 2025-10-05 12:00 | Alta
UX Testing & Optimization | Conduct user-experience tests & optimize the application’s performance | Víctor / Oswaldo | 2025-10-05 12:00 | 2025-10-05 13:00 | Media
Break & Mentor Feedback | Break & feedback from mentors to resolve questions & improve the project | Todos | 2025-10-05 13:00 | 2025-10-05 14:00 | Baja
Educational Capsules | Write scripts & generate three educational capsules using TTS | Víctor / Isay | 2025-10-05 14:00 | 2025-10-05 15:30 | Media
Final Pitch Deck | Prepare the pitch deck & final visual materials for the presentation | Isay / Víctor | 2025-10-05 15:30 | 2025-10-05 17:00 | Alta
Pitch Rehearsal | Rehearse the final pitch & demo in front of mentors | Todos | 2025-10-05 17:00 | 2025-10-05 18:00 | Media
Presentation & Closing | Present to the jury & officially close the event | Todos | 2025-10-05 18:00 | 2025-10-05 20:00 | Baja
README & Demo Video | Draft the final README & record the project’s demonstration video | Víctor / Isay | 2025-10-05 20:00 | 2025-10-05 22:30 | Alta
Project Delivery | Submit the final project on the NASA portal before the deadline | Víctor | 2025-10-05 22:30 | 2025-10-05 23:59 | Crítica